## Slide 1: French Translation of RDA Update on the Project
  Françoise Bourdon
  Bibliothèque nationale de France
  Pat Riva
  Bibliothèque et Archives nationales du Québec
  IFLA Satellite Meeting
  August 12, 2011
Notes: Françoise is not able to be with us today.

## Slide 2: RDA Ressources : description et accès
Partnership and organisation
Translation principles and methodology
Timeline
Examples of issues
Notes: RDA's French title is RDA, Ressources : description et accès. This title was chosen to retain the same acronym in both languages.
We've prepared our status report on the French translation project around the four themes of
Partnership + Organisation,
Translation Principles + Methodology,
Timeline,
and Issues.
Themes which either highlight the special aspects of our translation effort or which may have some analogies for some of the other language translations in progress or planned.

## Slide 3: Partners
1 association + 3 national libraries and others
  Association pour l’avancement des sciences et des techniques de la documentation (ASTED)
  Bibliothèque nationale de France (BnF)
  Bibliothèque et Archives nationales du Québec (BAnQ)
  Library and Archives Canada (LAC)
  + volunteers from Belgium
Editorial committee
  Meets by monthly videoconference
  Supported by translation teams
Notes: That our partnership involves 1 association, 3 national libraries (in 3 cities in 2 countries on 2 continents, 2 timezones) and additional volunteers from a third country, is just an indication of the logistical and organisational complexities of our project.
ASTED (Canada's French-language library association) has long been the publisher of French-language translations of AACR and provides the publishing support for the project.
Our 3 libraries have in the past been involved in translations of AACR and ISBD etc., either solo or together.
Our formal partnership is joined by Belgian librarians, first from Université catholique de Louvain, then Université de Liège, in an informal capacity.
The 4 formal partners each have 3 representatives on the Editorial Committee, chaired by the Executive Director of ASTED.
We meet, generally monthly, by videoconference. This remains one of the logistical challenges. Videoconference installations need to be booked in advance, and there is the potential for system incompatibility between our 3 sites (Asted members attend the meetings at BAnQ's offices). In fact, we have had more or less severe technical difficulties at each of our 8 meetings to date.
The members of the Editorial Committee are supported by translation teams within each partner's organisation.

## Slide 4: Translation Principles
Translate only into mother tongue
Review drafts by a partner in the other continent
  ensures the usability of the text by cataloguers of all the partner countries and the avoidance of regional terminology
Remain faithful to the text, but adapt instructions assuming use in a French-language cataloguing agency
  References to IFLA documents
  Examples
Notes: At the outset we established two principles:
- All translators translate into their mother tongue, thus all translators are native speakers of French. For the Canadian partners this has constrained the staff who can participate at the translation stage, although some of us others participate in different ways (such as on the Editorial Committee, or in work on adapting examples, or as consultants).
Translators also require a solid command of English, in particular the technical jargon of cataloguing, to be able to convey the true intent of the RDA text.
- French as spoken in France and in Canada is largely, but not entirely the same. To eliminate regional usages in the translation, we are planning on having crossed revision of chapters: those translated in Europe will be revised in Canada and those translated in Canada will be revised in Europe.
The goal is a text that is equally usable by cataloguers in both countries, and hopefully by other French-speaking countries as well.
- We also determined that our goal is not a literal translation of RDA, but the production of a cataloguing content standard intended to be applied by a cataloguing agency producing a French-language catalogue. (Same relationship as between RCAA2 and AACR2)
This means, for instance, referring to French-language translations of IFLA documents (FRBR, FRAD, ICP), and adapting examples, and changing the word “English” to “French” in instructions when it is there because it is standing in for the language of the cataloguing agency.

## Slide 5: Methodology
Started with Content type, Media type, Carrier type terms
Glossary, terms and definitions
Recurring phrases
    Apply the instructions given under …
"Test" chapters
Translation phase
Revision phase
PDFs from ALA Publishing for proofreading
Notes: We determined to start the translation process by agreeing on terminology, particularly the lists of Content type, Media type, Carrier type terms, then the rest of the Glossary (terms and definitions). Simultaneously we worked on translations for recurring phrases (83 of these identified by Marg Stewart).
For example “Apply the instructions given under (rule number)”
rendered as “Appliquer les instructions données sous…”
- At BAnQ we worked on these as a group with the whole translation team and this really helped ensure both greater understanding of the RDA text and of the style to adopt for the translation.
- In parallel, early on BnF and BAnQ did draft translations of “test” chapters for a technical test – can the translation template files be manipulated by our respective computer systems and wordprocessor versions and yet be successfully ingested by the Toolkit? We did not want to wait to the last minute to find this out!
BnF's test was chapter 0, and this proved to be another excellent source of terminology and style for later work. It also revealed early on some of the adaptation issues previously mentionned.
The test chapters showed us the utility of looking closely at the PDF output from the Toolkit as a method of proofreading and checking our work.
- At this point the partners are making progress on the translation phase proper, and next we will be in a revision phase, followed by a detailed proofreading phase.
One of the challenges at this phase is that it is hard to divise a process for commenting on or amending in-progress translations in the template format.

## Slide 6: Sharing the Work
Chapters (Sections) claimed by each partner
Done by staff in the 3 national library partners
  BnF : standards and cataloguing librarians
  BAnQ : cataloguing librarians
  LAC : standards and cataloguing librarians
Done by a professional translator on behalf of ASTED
  Examples adapted for a French catalogue by BAnQ
Notes: It was important to divide up the work fairly and according to each partner's strengths and capacity. This worked quite well organically. Each partner claimed chapters or sections.
Just to note that the 3 national library partners have done the work by contributing staff time.
ASTED, as an association with a very small staff, hired a professional translator (technical translator) to ensure its contribution. However, most examples cannot be adapted by a non-cataloguer, so BAnQ included completing the examples in these sections as part of its contribution.
The technical translator will also be used for the Toolkit interface translation.

## Slide 7: Timeline
Aug. 10, 2010, first meeting in Gothenburg
June 2011, final Glossary and Phrases
July 2011, first translations ready for revision
October 2011, last translations due
Early 2012, end of revision phase
Testing in the Toolkit and adjustments
Ongoing, integration of amendments
Notes: While we had some informal discussions much earlier (I remember speaking to Françoise about RDA as early as IFLA 2008 in Quebec), the first meeting of representatives of the 4 partners was held just 1 year ago in Gothenburg.
Due to the great need in Canada for a French translation to allow RDA implementation nationally (as in Marg's report earlier today), we set an ambitious initial timeline which has since been revised as we monitor RDA implementation plans.
We started on the Terms, Glossary and Phrases in fall 2010, and approx 70% was not particularly contentious, however, making decisions (and also compromises) about the last few terms took us into June 2011.
One of the difficult terms was, in fact, Media (as in Media type) and also “unmediated”...
Possibly in parallel with our revision phases, we will be testing the integration of French into the Toolkit and making final adjustments.
One challenge we were not expecting to face so soon, will be the translation and integration of changes to the text. We knew that there would eventually be amendments, but now we are expecting to need to evaluate and integrate textual changes recommended following the US National Test, and this even before the first release of RDA in French.

## Slide 8: Issues
French usage
  “City, town” should this be:
    Ville, commune or
    Ville, municipalité
Some examples do not work once adapted
    Several in chapters 16 (Places) and 11 (Corporate Bodies)
    Some also in chapter 6 (Works and expressions)
Internationalisation is incomplete
  For example, Appendix A for capitalisation
Notes: In addition to some terms for which consensus was difficult, we have started identifying a variety of other translation and adaptation issues:
- So far regional usage of French has not been as big an issue as we might have thought, but one phrase in the glossary caught us by surprise:
A town, city, province, state, and/or country in which a person resides or has resided.
Initially rendered as: Commune, ville, province, région administrative et/ou pays où une personne réside ou a résidé.
clear in Europe, but not in Canada, so modified to
Municipalité, ville, province, État et/ou pays où une personne réside ou a résidé
- There has also been some difficulty with examples that once adapted for a French language catalogue do not illustrate the section any more, particularly for access points.
For instance in ch.6 (Works and expressions)
6.2.2.5 Exception for Classical and Byzantine Greek works, choose a well-established form in the language of the agency (else use Latin or original Greek). Some works have such a title in English, but not in French:
Battle of the frogs and the mice but not Guerre des grenouilles et des rats (renvoi à la BnF) ou Batrachomyomachie (forme retenue à la BnF)
Synopsis historike Exemple à retirer de cette section puisqu’il y a un titre latin : Compendium chronicum

## Slide 9: Editorial Committee Members
Francine Benoit-Plamondon
Clément Arsenault
Élaine Ménard
Yves Alix
Françoise Bourdon
Françoise Leresche
Aline Locker
Danielle Poirier
Lucie Pellerin
Pat Riva
Pierre Gamache
Antonio Lechasseur
Marg Stewart
Notes: Several in ch.16 (Places)
Livorno/Leghorn
(English form no longer in common usage, no such change in French)
Romania/Roumania
(Variant spellings in English, only one spelling Rumanié, in French)
Others in ch.11 (Corporate bodies)
11.2.2.52 : example of Swiss National Library (selection of German form because none of the forms matches the language of the catalogue) does not work for a French-language catalogue as there is an official French language form of the name.
We need to identify additional examples for these sections.
- Although RDA has eliminated much of AACR2 English-language bias and taken steps towards greater internationalisation, some residues remain.
One striking example is the structure of Appendix A, Capitalization, which starts with detailed instructions on English capitalisation rules, and the rules for all other languages are presented as differences from the English rules, rather than standing on their own. Much more difficult to use in a non-English language environment.
The translation work brings these points to our attention, and will allow us to raise them with JSC as appropriate.
**To end, here is the list of current members of the Editorial Committee